## RF and GPS test detailed plan
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
6:00
7:00 |  |  | Setup and meaure distance to place laser. Fly at 25 m - 125 m horizontal, 5 m - 50 m vertical from controlling station. Stay at each position for 20 sec. |  | Setup and meaure distance to place laser. Fly at 25 m - 125 m horizontal, 5 m - 50 m vertical from controlling station. Stay at each position for 20 sec.
8:00 |  | Briefing OSU campus. | Change battery if needed. Meaure distance to setup laser. Fly at 150 m - 250 m horizontal, 5 m - 50 m vertical from controlling station. Stay at each position for 20 sec. |  | Change battery if needed. Meaure distance to setup laser. Fly at 150 m - 250 m horizontal, 5 m - 50 m vertical from controlling station. Stay at each position for 20 sec.
9:00 | Depart Lincoln
10:00
11:00
12:00 |  | System Test: check GPS and RF readings, meaure distance to setup laser. |  |  |  | Depart Stillwater
13:00 |  | Fly at 25 m horizontal 5 m and 10 m vertical from controlling station. Stay at each position for 30 sec. Land, analyze results and attempt to apply any required offset for gps. |  | Setup and meaure distance to place laser. Fly at 25 m - 125 m horizontal, 5 m - 50 m vertical from controlling station. Stay at each position for 20 sec.
14:00 |  | Fly at 25 m horizontal 15 m - 50 m vertical from controlling station. Fly at 50 m - 250 m horizontal, 5 m - 50 m vertical from controlling station. Stay at each position for 30 sec. |  | Change battery if needed. Meaure distance to setup laser. Fly at 150 m - 250 m horizontal, 5 m - 50 m vertical from controlling station. Stay at each position for 20 sec.
15:00 | Arrive Stillwater
16:00
17:00
18:00 | [5 empty] | Arrive Lincoln
19:00 | Hideaway Pizza | Analyze Data and perform any required change/maintenance. | Analyze Data and perform any required change/maintenance. | Analyze Data and perform any required change/maintenance. | Analyze Data and perform any required change/maintenance.
20:00
21:00
22:00
23:00

## plan A and B
A | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
AM |  |  | RF and GPS tests |  | RF and GPS tests
| Depart Lincoln | Briefing OSU campus. | RF and GPS tests |  | RF and GPS tests | Debrief OSU campus
PM |  | System Test: RF and GPS tests check and setup |  | RF and GPS tests |  | Depart Stillwater
| Arrive Stillwater | RF and GPS tests |  | RF and GPS tests
Evening | Hideaway Pizza | Analysis/modification/maintenance | Analysis/modification/maintenance | Analysis/modification/maintenance | Analysis | Arrive Lincoln
B | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
AM |  |  | RF and GPS tests |  | RF and GPS tests
| Depart Lincoln | Briefing OSU campus. |  | RF and GPS tests |  | Debrief OSU campus
PM |  | System Test: RF and GPS tests check and setup | RF and GPS tests |  | RF and GPS tests | Depart Stillwater
| Arrive Stillwater | RF and GPS tests |  | RF and GPS tests
Evening | Hideaway Pizza | Analysis/modification/maintenance | Analysis/modification/maintenance | Analysis/modification/maintenance | Analysis | Arrive Lincoln